## Application Run Team
Application Migration Runbook (Checklist)
Phase | Task | Ownership | Dates/Weeks of | NOTES
Development | Install IIS and MSSQL
Development | Configure IIS and MSSQL
Development | Network Security Group Changes
Development | Install APP and Database (Server software)
Development | Import data (DB Restore copy of Prod DB)
Development | Configure APP/C Server (including certs)
Development | Install and Configure APP Client ( and Azure side clients)
Development | Configure Load balancer (validate Cert Needs)
Development | Configure On prem Sever ( Side)
Development | Firewall Changes
Development | Update DNS
Validation | Check that hostname and IP resolve properly
Validation | validate USER access (Application Admins using IE from workstations)
Validation | Check SSL certs (invoke SSL between SN & APP)
Validation | DMNE Client functionality (access, local profile, master profile -across ESL's)
Validation | Connectivity of Application (update jobs, check in times, etc.)
Validation | validate connection to profile shares from APP and updates to master profiles
Validation | validate new user creation
Approval | Agency business approval/signoff
Approval | Initiate security scans
Application - PROD | Stand up APP and Database Servers
Application - PROD | Import data (DB Restore copy of Prod DB)
Application - PROD | Configure APP/C Server (including certs)
Application - PROD | Configure Load balancer (validate Cert Needs)
Application - PROD | Network Security Group Changes
Application - PROD | Initiate Security Scans
Application - PROD | Azure Monitoring
Application - PROD | Azure Logging
Application - PROD | Azure Backup
Application - PROD | Operations & Readiness Review - Plus RACI
Application - PROD | ATO
Cutover Go live actions/tasks | Firewall Changes
Cutover Go live actions/tasks | Take Application off line
Cutover Go live actions/tasks | Stop APP Services at Data Center
Cutover Go live actions/tasks | Copy production DB, move to Azure, Import data (DB Restore copy of Prod DB)
Cutover Go live actions/tasks | Start APP Services at Azure
Cutover Go live actions/tasks | Transition Load Balancer (Shut done Data Center LB and turn on Azure LB)
Cutover Go live actions/tasks | Restart Application
Cutover Go live actions/tasks | Update DNS
Validation | Check that hostname and IP resolve properly
Validation | validate NMC access (Application Admins using IE from workstations)
Validation | Check SSL certs (invoke SSL between SN & APP)
Validation | APP Client functionality (access, local profile, master profile -across ESL's)
Validation | Connectivity of Application (update jobs, check in times, etc.)
Validation | validate new user creation
Approval | Agency business approval/signoff
Application - PROD - Recovery | Firewall Changes
Application - PROD - Recovery | Take APP off line
Application - PROD - Recovery | Stop APP Services at Azure
Application - PROD - Recovery | Turn Off VMs on Azure
Application - PROD - Recovery | Turn on VMs at Data Center
Application - PROD - Recovery | Start APP Services at Data Center
Application - PROD - Recovery | Transition Load Balancer (Shut down Azure LB and turn on Data Center LB)
Application - PROD - Recovery | Update DNS
Validation | Check that hostname and IP resolve properly
Validation | validate USER access (Application Admins using IE from workstations)
Validation | Check SSL certs (invoke SSL between SN & APP)
Validation | APP Client functionality (access, local profile, master profile -across ESL's)
Validation | Connectivity of Application (update jobs, check in times, etc.)
Validation | validate connection to profile shares from APP and updates to master profiles
Validation | validate new user creation